## Sheet1
Calculation of the amount of time we can reasonably expect to have for Early Science Operations
Days
Months | 9 | 30 | 270
Assume 25 days total shut-down in Feb to change over to permanent power and
Shutdowns | 1 | 25 | 245 | upgrade to software revision 9.0. Probably do some array reconfiguration too.
Hours
Hours/day |  | 16 | 3920 | Assumes say 5pm to 9am operation and 9am to 5pm engineering/maintenance using the array
(Main work day starts at 8am but 1 hour to get ready and drive up.)
Computing check |  | 0.94643 | 3710 | Regression testing once per week for 6 hours
Weather loss |  | 0.75 | 2782.5 | This is pessimistic but period does include the Altiplanic winter.
Faults |  | 0.75 | 2086.875 | Recall that we are only counting faults that actually stop observations or wreck the data
Nominal fraction |  | 0.333 | 694.9294 | Arbitrary but this was the figure approved by the Board
Time on sky |  | 0.667 | 463.5179 | This may be optimisitic at this stage if Calibration and all software overheads are included but
this depends on the nature of the project: simpler observations should have lower overheads
Hours
Time available for Early Science |  |  | 694.9294 | This is our interpretation of the definition - i.e. overheads are included
In round terms this is 80 hours per month |  |  |  | Most typical observation in this period will be a map or small mosaic and so
UV coverage is more important that sensitivity
|  |  | Hours | So this is of order 100 sets of data with +/-3.5 hours of HA coverage
Time for CSV |  |  | 1391.9456 | Based on experience so far we believe that this will be adequate to keep the Commissioning on track
So roughly 160 hours per month