## Sheet1
|  | As of April 5, 2010 | Date to |  | Original
High Speed EVLA Sampler schedule |  |  | Complete | Coordinator | Date
1. Generate specification for channel-to-channel cross-talk |  |  | Complete | Jackson/Perley | Complete
on the sampler/demux board
2. Verify that Altera can provide the "AltGXB" mega-function |  |  | Complete | Revnell | Complete
in the FPGA for the demux design
3. Verify that Altera completely understands NRAO's clock |  |  | Complete | Revnell | Complete
phasing requirements for the demux design
4. Complete a successful Altera FPGA place-and-route |  |  | Complete | Revnell | Complete
* 5. Define WIDAR/antenna tests for prototype samplers |  |  |  | Rupen
* 6. Complete fabrication of prototype sampler board with |  |  | Complete | Durand/Revnell | Complete
demultiplexer based on Altera FPGA - 12/18/09 - Revnell
7. Receive 4 FPGAs for initial installation |  |  | Complete | Durand/Shores | Complete
* 8. Place order for 4+ sampler boards |  |  | 2010-04-15 | Durand/Revnell | 2010-04-15
(i.e. enough to populate 4 DTS modules)
* 9. Verify laboratory performance of new prototype sampler board |  |  | 2010-05-20 | Durand/Revnell | 2010-05-20
*10. Complete fabrication of 4 sampler boards (RFI Testing) |  |  | 2010-06-01 | Durand/Revnell | 2010-06-01
11. Start procurement process for Board production contract |  |  | 2010-06-30 | Durand/Shores | 2010-06-30
*12. Install sampler boards in DTS modules and |  |  | 2010-06-30 | Durand/Shores | 2010-06-30
install one each in 4 EVLA antennas ( one IF by 4 antennas)
*13. Complete WIDAR tests of sampler boards in EVLA antennas |  |  | 2010-08-14 | Rupen | 2010-07-14
*14. Place production order for sampler boards |  |  | 2010-08-21 | Durand/Revnell | 2010-07-21
Requires successful completion of WIDAR Tests, Item 13
*15. Complete the DTS ICD |  |  | 2010-09-11 | Shores | 2010-08-11
16. Production sampler boards delivered to Socorro |  |  | 2010-12-21 | Shores | 2010-11-21
*17. Begin installation of upgraded DTS modules |  |  | 2011-01-15 | Gerrard | 2010-12-15
*17. Complete installation of upgraded DTS modules |  |  | 6/31/2011 | Gerrard | 2011-05-01
Requires significant effort